## Sheet1
TAX INVOICE
To, |  | Date : 05-05-2026
NEO ITURKAA ENTERPRISES. |  | Invoice No. 004/2026-27
ADD :- Office:- 101 1st Floor, Arihant Royale, Vaishali Nagar,
Balrajeshwar Marg, Mulund (west) Mumbai :- 400080
Pan No. : AAJFN6629D
GST No. : 27AAJFN6629D1Z5
Name of Work:-Reainforcemant Work.
Name Of Project :- Tower D Wing Galaxy Maplewood -Airoli.
Subject :- REF NO. : 20
Sr. No. | Description | Amount
1 | 37Th Slab Reinforcement Work done Amount | 340000
2 | Taxable Amount
| Add CGST@9% | 30600
| Add SGST@9% | 30600
| Net Payable Amount | 401200
NAME :- RCR ENTERPRISES FOR |  | RCR ENTERPRISES
A/C :- 088405500559
IFSC :- ICIC0000884
AUTHORISED SIGNATORY

## Sheet2
`
To, | [7 empty] | Date : 05-05-2026
NEO ITURKAA ENTERPRISES. | [7 empty] | Invoice No. 004/2026-27
ADD :- Office:- 101 1st Floor, Arihant Royale, Vaishali Nagar,
Balrajeshwar Marg, Mulund (west) Mumbai :- 400080
Name Of Project :- Tower D Wing Galaxy Maplewood -Airoli.
Name of Work:-Reainforcemant Work.
Subject :- REF NO. : 20
W. O. No. :-GALAXY/NEOITURKAA/2025-26/06
Sr. No | Description | Unit | W.O. | Rate | Previous | This Bill | Cumulative | Previous | This Bill | Previous
|  |  | Qty. |  | Quantity | Quantity | Quantity | Amount | Amount | Amount
1 | Reinforcement Work Done. | Sft. | 184464 | 49.6032 | 7110000 | 340000 | 7450000 | 7110000 | 340000 | 7450000
2 | Dept. Fitter Supply. | Nos. |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0
3 | Dept. Fitter Helper Supply. | Nos. |  | 800 | 0 | 0 | 0 | 0 | 0 | 0
| Total Amount | [6 empty] | 7110000 | 340000 | 7450000
ADD CGST @9%
ADD CGST @9%
| LESS RETENTION@3% | [6 empty] | 213300 | 10200 | 223500
.
| Gross Amount | [6 empty] | 6896700 | 329800 | 7226500
| TDS 1% Less amount | [7 empty] | 3400
| Balance | [7 empty] | 326400

## Tower C Wing
NEO ITURKAA ENTERPRISES.
Name of Work:-Reainforcemant Work.
Subject :- REF NO. : 20
BUA Building -
Approximate Area
| CIVIL WORK | Sft | 184464 |  | @ | 49.6032 |  | 9150000
Sr. | Particulars | Part | Work done |  |  | Amount
No. | of item
| Reainforcemant |  | Previous | This Bill | Cumulative | Previous | This Bill | Cumulative
| Work |  | Quantity | Quantity | Quantity | Amount | Amount | Amount
1 | 16th slab | 310000 | 100% | 0% | 100% | 310000 | 0 | 310000
2 | 17th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
3 | 18th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
4 | 19th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
5 | 20th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
6 | 21st slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
7 | 22nd slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
8 | 23rd slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
9 | 24th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
10 | 25th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
11 | 26th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
12 | 27th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
13 | 28th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
14 | 29th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
15 | 30th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
16 | 31st slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
17 | 32nd slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
18 | 33rd slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
19 | 34th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
20 | 35th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
21 | 36th slab | 340000 | 100% | 0% | 100% | 340000 | 0 | 340000
22 | 37th slab | 340000 | 0 | 100% | 100% | 0 | 340000 | 340000
23 | 38th slab | 340000 | 0 | 0 | 0 | 0 | 0 | 0
24 | 39th slab | 340000 | 0 | 0 | 0 | 0 | 0 | 0
25 | Completion of Terrace Slab 40th slab | 340000 | 0 | 0 | 0 | 0 | 0 | 0
26 | Completion of LMR, OHWT PARAPET WALL. | 680000 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL AMOUNT | 9150000 | 2100% | 100% | 2200% | 7110000 | 340000 | 7450000

## supply
NEO ITURKAA ENTERPRISES.
Labour's Supply MARCH 2026 | [7 empty] | Date : 05-05-2026
Contractar : - RCR ENTERPRISES
Date | Challan No. | Description Contract basis work | Fitter | Hours | Total Fitter Hours | Fitter Helfar | Hours | Total Lebour Hours | Remarks
|  | Total (Nos) |  |  | 0 |  |  | 0
|  |  |  | FITTER |  | FITTER HELFAR
|  | Nos |  | 0 |  | 0
|  | Rate |  | 1100 |  | 800
|  | TOTAL AMOUNT |  | 0 |  | 0 |  | 0

## Balance sheet
SR. NO | DATE | RA BILLS | BILL AMOUNT | RETENTION 3% | AMOUNT | ACCOUNT CREDITED | 1%TDS BALANCE | ADVANCE | BALANCE | GST AMOUNT | BALANCE
1 | 2025-07-10 |  |  |  |  | 150000
2 | 2025-08-04 |  |  |  |  | 200000
05-08-2025 BILL NO.01 DIGHA GALAXY.
|  |  | 650000 | 19500 | 630500 |  | 6500 |  |  | 117000
| TOTAL AMOUNT |  | 650000 | 19500 | 630500 | 350000 | 6500 | 356500 | 274000 | 117000 | 391000
3 | 2025-08-20 |  |  |  |  | 394250
22-08-2025 BILL NO.02 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 990000 | 29700 | 960300 | 744250 | 9900 | 754150 | 206150 | 178200 | 384350
04-09-2025 BILL NO.03 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 1330000 | 39900 | 1290100 | 744250 | 13300 | 757550 | 532550 | 239400 | 771950
4 | 17/09/2025 |  |  |  | NEFT | 384350
16-09-2025 BILL NO.04 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 1670000 | 50100 | 1619900 | 1128600 | 16700 | 1145300 | 474600 | 300600 | 775200
5 | 24/09/2025 |  |  |  | NEFT | 387600
10-10-2025 BILL NO.05 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 2010000 | 60300 | 1949700 | 1516200 | 20100 | 1536300 | 413400 | 361800 | 775200
6 | 2025-06-10 |  |  |  | NEFT | 387600
23-10-2025 BILL NO.06 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 2350000 | 70500 | 2279500 | 1903800 | 23500 | 1927300 | 352200 | 423000 | 775200
7 | 29/10/2025 |  |  |  | NEFT | 387600
04-11-2025 BILL NO.07 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 2690000 | 80700 | 2609300 | 2291400 | 26900 | 2318300 | 291000 | 484200 | 775200
8 | 14/11/2025 |  |  |  | NEFT | 397800
16-11-2025 BILL NO.08 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 3030000 | 90900 | 2939100 | 2689200 | 30300 | 2719500 | 219600 | 545400 | 765000
9 | 20/11/2025 |  |  |  | NEFT | 377400
27-11-2025 BILL NO.09 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 3370000 | 101100 | 3268900 | 3066600 | 33700 | 3100300 | 168600 | 606600 | 775200
10 | 2025-09-12 |  |  |  | NEFT | 387600
12-12-2025 BILL NO.10 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 3710000 | 111300 | 3598700 | 3454200 | 37100 | 3491300 | 107400 | 667800 | 775200
11 | 19/12/2025 |  |  |  | NEFT | 387600
21-12-2025 BILL NO.11 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 4050000 | 121500 | 3928500 | 3841800 | 40500 | 3882300 | 46200 | 729000 | 775200
29-12-2025 BILL NO.12 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 4390000 | 131700 | 4258300 | 3841800 | 43900 | 3885700 | 372600 | 790200 | 1162800
12 | 2026-01-01 |  |  |  | NEFT | 387600
07-01-2026 BILL NO.13 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 4730000 | 141900 | 4588100 | 4229400 | 47300 | 4276700 | 311400 | 851400 | 1162800
13 | 20/01/2026 |  |  |  | NEFT | 775200
14 | 22/01/2026 |  |  |  | NEFT | 387600
01-02-2026 BILL NO.14 DIGHA GALAXY.
|  |  | 680000 | 20400 | 659600 |  | 6800 |  |  | 122400
| TOTAL AMOUNT |  | 5410000 | 162300 | 5247700 | 5392200 | 54100 | 5446300 | -198600 | 973800 | 775200
15 | 2026-10-02 |  |  |  | NEFT | 775200
09-02-2026 BILL NO.15 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 5750000 | 172500 | 5577500 | 6167400 | 57500 | 6224900 | -647400 | 1035000 | 387600
20-02-2026 BILL NO.16 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 6090000 | 182700 | 5907300 | 6167400 | 60900 | 6228300 | -321000 | 1096200 | 775200
16 | 27/02/2026 |  |  |  | NEFT | 387600
07-03-2026 BILL NO.17 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 6430000 | 192900 | 6237100 | 6555000 | 64300 | 6619300 | -382200 | 1157400 | 775200
17 | 2026-03-10 |  |  |  | NEFT | 387600
18 | 2026-03-20 |  |  |  |  | 387600
27-03-2026 BILL NO.18 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 6770000 | 203100 | 6566900 | 7330200 | 67700 | 7397900 | -831000 | 1218600 | 387600
09-04-2026 BILL NO.19 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 7110000 | 213300 | 6896700 | 7330200 | 71100 | 7401300 | -504600 | 1279800 | 775200
19 | 2026-04-16 |  |  |  | NEFT | 387600
05-05-2026 BILL NO.20 DIGHA GALAXY.
|  |  | 340000 | 10200 | 329800 |  | 3400 |  |  | 61200
| TOTAL AMOUNT |  | 7450000 | 223500 | 7226500 | 7717800 | 74500 | 7792300 | -565800 | 1341000 | 775200