## Sheet1
TAX INVOICE
To, |  | Date : 05-05-2026
SSHIVAAY CONSTRUCTIONS. |  | Invoice No. 007/2026-27
ADD :- Office:- SANT KRUPA CHS LTD., FLAT NO.5, PLOT NO. 78, SECTOR - 19
NERUL (EAST), NAVI MUMBAI - 400706
Pan No. : AEXFS8040P
GST No. : 27AEXFS8040P1ZW
Name of Work:-Reainforcemant Work.
Name Of Project :- BMC COLONY, BUILDING NO :- S3 VIKHROLI, MUMBAI
Subject :- REF NO. : 01
Sr. No. | Description | Amount
1 | 15Th To 16Th Slab Reinforcement Work done Amount | 250648
2 | Taxable Amount
| Add CGST@9% | 22558.32
| Add SGST@9% | 22558.32
| Net Payable Amount | 295764.64
NAME :- RCR ENTERPRISES FOR |  | RCR ENTERPRISES
A/C :- 088405500559
IFSC :- ICIC0000884
AUTHORISED SIGNATORY

## Sheet2
`
To, | [7 empty] | Date : 05-05-2026
SSHIVAAY CONSTRUCTIONS. | [7 empty] | Invoice No. 007/2026-27
ADD :- Office:- SANT KRUPA CHS LTD., FLAT NO.5, PLOT NO. 78, SECTOR - 19
NERUL (EAST), NAVI MUMBAI - 400706
Name Of Project :- BMC COLONY, BUILDING NO :- S3 VIKHROLI, MUMBAI
Name of Work:-Reainforcemant Work.
Subject :- REF NO. : 01
W. O. No. :-PARKSITE/SSHIVAAY/2026-27
Sr. No | Description | Unit | W.O. | Rate | Previous | This Bill | Cumulative | Previous | This Bill | Previous
|  |  | Qty. |  | Quantity | Quantity | Quantity | Amount | Amount | Amount
1 | S2 Reinforcement Work Done. | Sft. | 314554 | 53 | 0 | 0 | 0 | 0 | 0 | 0
2 | S3 Reinforcement Work Done. | Sft. | 24750 | 52 | 0 | 4674 | 4674 | 0 | 243048 | 243048
3 | Dept. Fitter Supply. | Nos. |  | 1100 | 0 | 6 | 6 | 0 | 6600 | 6600
4 | Dept. Fitter Helper Supply. | Nos. |  | 800 | 0 | 1.25 | 1.25 | 0 | 1000 | 1000
| Total Amount | [6 empty] | 0 | 250648 | 250648
ADD CGST @9%
ADD CGST @9%
| LESS RETENTION@0% | [6 empty] | 0 | 0 | 0
.
| Gross Amount | [6 empty] | 0 | 250648 | 250648
| TDS 1% Less amount | [7 empty] | 2506.48
| Balance | [7 empty] | 248141.52

## Tower S2 Wing
SSHIVAAY CONSTRUCTIONS.
Name of Work:-Reainforcemant Work.
Subject :- REF NO. : 01
BUA Building - S2 BUILDING
Approximate Area
| CIVIL WORK | Sft | 314554 |  | @ | 53 |  | 16671362
Sr. | Particulars | Part | Work done |  |  | Amount
No. | of item
| Reainforcemant |  | Previous | This Bill | Cumulative | Previous | This Bill | Cumulative
| Work |  | Quantity | Quantity | Quantity | Amount | Amount | Amount
1 | Raft Footing, Plint Beam | 22728 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1st slab | 17068 | 0 | 0 | 0 | 0 | 0 | 0
3 | 2nd slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3rd slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
5 | 4th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
6 | 5th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
7 | 6th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
8 | 7th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
9 | 8th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
10 | 9th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
11 | 10th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
12 | 11th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
13 | 12th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
14 | 13th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
15 | 14th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
16 | 15th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
17 | 16th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
18 | 17th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
19 | 18th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
20 | 19th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
21 | 20th slab Refuge | 11946 | 0 | 0 | 0 | 0 | 0 | 0
22 | 21st slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
23 | 22nd slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
27 | Completion of Terrace Slab 23th slab | 11946 | 0 | 0 | 0 | 0 | 0 | 0
28 | Completion of LMR, OHWT PARAPET WALL. | 11946 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 298855.8 | 18971
| TOTAL AMOUNT | 314554 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17068
[9 empty] | 262816.8 | 36039
11946.2182

## Tower S3 Wing
SSHIVAAY CONSTRUCTIONS.
Name of Work:-Reainforcemant Work.
Subject :- REF NO. : 01
BUA Building -S3 BUILDING
Approximate Area
| CIVIL WORK | Sft | 24750 |  | @ | 52 |  | 1287000
Sr. | Particulars | Part | Work done |  |  | Amount
No. | of item
| Reainforcemant |  | Previous | This Bill | Cumulative | Previous | This Bill | Cumulative
| Work |  | Quantity | Quantity | Quantity | Amount | Amount | Amount
1 | 15th slab | 2750 | 0 | 2750 | 2750 | 0 | 143000 | 143000
2 | 16th slab | 2750 | 0 | 1924 | 1924 | 0 | 100048 | 100048
3 | 17th slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
4 | 18th slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
5 | 19th slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
6 | 20th slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
7 | 21st slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
11 | Completion of Terrace Slab 22th slab | 2750 | 0 | 0 | 0 | 0 | 0 | 0
12 | Completion of LMR, OHWT PARAPET WALL. | 2750 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL AMOUNT | 24750 | 0 | 4674 | 0 | 0 | 243048 | 243048

## supply
SSHIVAAY CONSTRUCTIONS.
Labour's Supply May 2026 | [7 empty] | Date : 05-05-2026
Contractar : - RCR ENTERPRISES
Date | Challan No. | Description Contract basis work | Fitter | Hours | Total Fitter Hours | Fitter Helfar | Hours | Total Lebour Hours | Remarks
2026-04-09 | 9 | 15th slab covring and slab Cheking work S3 building. | 2 | 8 | 16 | 0 | 0 | 0
2026-04-10 | 9 | 15Tth slab casting work complit 1 fitter and s2 building drain slab steel cutting banding fitter 4 | 4 | 8 | 32 | 1 | 10 | 10
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
|  | Total (Nos) |  |  | 48 |  |  | 10
|  |  |  | FITTER |  | FITTER HELFAR
|  | Nos |  | 6 |  | 1.25
|  | Rate |  | 1100 |  | 800
|  | TOTAL AMOUNT |  | 6600 |  | 1000 |  | 7600

## Balance sheet
SR. NO | DATE | RA BILLS | BILL AMOUNT | RETENTION 2% | AMOUNT | ACCOUNT CREDITED | 1%TDS BALANCE | ADVANCE | BALANCE | GST AMOUNT | BALANCE
1 | 2026-04-11 |  |  |  | CASH ANSAT | 15000
2 | 2026-04-18 |  |  |  | CASH ANSAT | 15000
3 | 2026-04-26 |  |  |  | CASH ANSAT | 15000
4 | 2026-05-09 |  |  |  | SANDIP ONLINE | 22500
5 | 2026-05-16 |  |  |  | NEFT | 141570
6 | 2026-05-23 |  |  |  | SANDIP ONLINE | 24000
7 | 2026-05-29 |  |  |  | NEFT | 99000
05-05-2026 BILL NO.01 VIKHROLI PARK SITE.
|  |  | 250648 | 0 | 250648 |  | 2506.48 |  |  | 45116.64
| TOTAL AMOUNT |  | 250648 | 0 | 250648 | 332070 | 2506.48 | 334576.48 | -83928.48 | 45116.64 | -38811.84